## Meetings (MOM)
MOM ID | Meeting Date | Branch / Location | Meeting Title / Subject | Meeting Type | Venue / Mode | Start Time | End Time | Meeting Lead By | MOM Prepared By | Attendees Present | Absent / Regrets | Agenda Points | Discussion Summary | Key Decisions Taken | Next Meeting Date | Total Tasks | Completed | Pending | Overdue | Completion %
MOM-001 | 2026-08-28 10:00 | Head Office - Mumbai | Monthly Business & Sales Review - Aug 2026 | Monthly Review | Executive Boardroom / Zoom | 10:00 AM | 11:45 AM | Rajesh Sharma (Director) | Pooja Patel (EA to Director) | Rajesh Sharma, Pooja Patel, Amit Shah, Rahul Mehta, Priya Nair | Karan Joshi (On Leave) | 1. August revenue target vs actual 2. Receivables above 90 days 3. Surat branch expansion plan | August sales closed at 94% of target with slight deficit from Surat branch. Receivables above 90 days were reviewed in detail; Accounts team instructed to circulate weekly ageing reports. Director gave in-principle approval for site survey for new branch. | Surat branch to submit sales turnaround plan; Finance to automate weekly receivables report; Approved budget for branch survey. | 2026-09-25 10:00
MOM-002 | 2026-09-04 14:00 | Tech Hub - Ahmedabad | MOM Assistant Backend & Multi-Language Audio Pipeline | Project Review | Tech Conference Room / Google Meet | 02:00 PM | 03:30 PM | Harmish (Tech Lead) | MOM Assistant AI | Harmish, Sneha Verma, Devendra Dave, Hardik Prajapati | None | 1. Whisper STT performance benchmarks 2. Gujarati & Hindi translation accuracy 3. Audio summary cache architecture | Successfully demonstrated sub-15 second audio processing using Groq STT and OpenAI fallback. Gujarati and Hindi multi-language translation and Edge TTS voice synthesizers passed audio clarity quality tests. | Adopt Groq as default STT with OpenAI Whisper fallback; Cache translated audio files on disk with SHA256 hashing. | 2026-09-18 14:00
MOM-003 | 2026-09-08 11:00 | Head Office - Mumbai | Corporate Excel Template Integration & Flutter Export | Planning Meeting | Room 302 / Microsoft Teams | 11:00 AM | 12:15 PM | Harmish (Lead) | MOM Assistant AI | Harmish, Priya Patel (Mobile Lead), Amit Shah (Backend Lead), Rahul Mehta (QA Lead) | Vikram Singh (Client Visit) | 1. Excel format integration (MOM Format_8986) 2. Master Excel workbook syncing across all meetings 3. Flutter UI one-tap export button | Reviewed corporate Excel template requirements. Agreed to support single-meeting formatted export as well as an automatically synced master Excel workbook that maintains an ongoing register of all meetings and actionable tasks. | Integrate ExcelJS in DocumentService; Automatically update MOM_Master_Tracker.xlsx whenever MOM is generated; Add Excel download card in Flutter UI. | 2026-09-22 11:00

## Tasks
Task ID | MOM ID | Meeting Date | Branch | Task / Action Point | Responsible Person | Following Person | Priority | Assigned Date | Target Deadline | Revised Deadline | Status | % Complete | Completion Date | Days Overdue (+) / Left (-) | Delay Reason | Reminder Action | Remarks | Key (system) | Overdue Flag (system)
T-001 | MOM-001 |  |  | Share 90+ days receivable ageing report with Director | Priya Nair | Pooja Patel | High | 2026-08-28 10:00 | 2026-09-02 |  | Completed | 100% | 2026-09-01 |  |  |  | Sent via email with dashboard
T-002 | MOM-001 |  |  | Submit Surat branch sales turnaround plan | Amit Shah | Rajesh Sharma | High | 2026-08-28 10:00 | 2026-09-10 |  | In Progress | 70% |  |  | Awaiting data from other dept. |  | Draft under final review
T-003 | MOM-001 |  |  | Conduct site survey for proposed new branch | Rahul Mehta | Rajesh Sharma | Medium | 2026-08-28 10:00 | 2026-09-20 |  | In Progress | 40% |  |  |  |  | Vendor quotes received
T-004 | MOM-002 |  |  | Implement Edge TTS Gujarati audio synthesis module | Devendra Dave | Harmish | High | 2026-09-04 14:00 | 2026-09-08 |  | Completed | 100% | 2026-09-07 |  |  |  | Deployed to staging server
T-005 | MOM-002 |  |  | Benchmark translation latency across OpenAI and Gemini | Sneha Verma | Harmish | Medium | 2026-09-04 14:00 | 2026-09-12 |  | In Progress | 80% |  |  |  |  | Report ready
T-006 | MOM-002 |  |  | Set up disk cleanup cron for temporary audio files older than 30 days | Hardik Prajapati | Harmish | Low | 2026-09-04 14:00 | 2026-09-16 |  | Not Started | 0% |  |  |  |  | Scheduled for Sprint 5
T-007 | MOM-003 |  |  | Implement master Excel tracker sync in DocumentService.js | Amit Shah | Harmish | High | 2026-09-08 11:00 | 2026-09-11 |  | In Progress | 90% |  |  |  |  | Template mapping complete
T-008 | MOM-003 |  |  | Update Flutter Export Document screen with Excel (.xlsx) option | Priya Patel | Harmish | High | 2026-09-08 11:00 | 2026-09-12 |  | Completed | 100% | 2026-09-09 |  |  |  | UI verified with green branding
T-009 | MOM-003 |  |  | Perform regression tests on formula calculations in Master Excel | Rahul Mehta | Harmish | High | 2026-09-08 11:00 | 2026-09-14 |  | Not Started | 0% |  |  |  |  | Test cases mapped
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Days Overdue (+) / Left (-) = IF(OR([Task ID]="",IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])=""),"",IF([Status]="Completed",IF([Completion Date]="","",[Completion Date]-IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])),IF([Status]="Cancelled","",TODAY()-IF([Revised Deadline]="",[Target Deadline],[Revised Deadline]))))
Reminder Action = IF([Task ID]="","",IF(OR([Status]="Completed",[Status]="Cancelled"),"Closed",IF(IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])="","Set deadline",IF(TODAY()>IF([Revised Deadline]="",[Target Deadline],[Revised Deadline]),"OVERDUE - Escalate",IF(IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])-TODAY()<=3,"Send Reminder","On Track")))))
Overdue Flag (system) = IF([Task ID]="",0,IF(OR([Status]="Completed",[Status]="Cancelled"),0,IF(IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])="",0,IF(TODAY()>IF([Revised Deadline]="",[Target Deadline],[Revised Deadline]),1,0))))

## MOM Print
MINUTES OF MEETING
Enter MOM ID: | MOM-003 | <-- type / pick the MOM ID here, everything below fills in automatically
Meeting Date | 2026-09-01 | Branch / Location | Head Office
Meeting Title | Monthly Business Review - Aug 2026 | Meeting Type | Monthly Review
Venue / Mode | Conference Room / Zoom | Next Meeting Date | 2026-10-01
Start Time | 11:00 AM | End Time | 12:30 PM
Meeting Lead By | Mr. Director | MOM Prepared By | EA to Director
ATTENDEES PRESENT
Mr. A. Shah, Ms. P. Patel, Mr. R. Mehta
ABSENT / REGRETS
Mr. K. Joshi (on leave)
AGENDA POINTS
1. Aug sales review 2. Pending receivables 3. New branch proposal
DISCUSSION SUMMARY
Aug sales closed at 92% of target; shortfall mainly from Surat branch. Receivables above 90 days discussed - Accounts to share ageing report. Director approved in-principle survey for the new branch.
KEY DECISIONS TAKEN
Surat branch to submit recovery plan; ageing report to be circulated weekly.
ACTION POINTS / TASK LIST
Task ID | Task / Action Point | Responsible Person | Following Person | Priority | Deadline | Status | Completion
T-001 | Share 90+ days receivable ageing report with Director | Ms. P. Patel | EA to Director | High | 2026-09-05 | Completed | 100%
T-002 | Submit Surat branch sales recovery plan | Mr. R. Mehta | Mr. A. Shah | High | 2026-09-08 | In Progress | 60%
T-003 | Site survey report for proposed new branch | Mr. K. Joshi | EA to Director | Medium | 2026-09-20 | Not Started | 0%
Prepared by: | EA to Director |  | Approved by: | Mr. Director
Note: only the first 15 action points of a meeting are shown here. See the Tasks sheet for the complete list.