## Meetings (MOM)
MOM ID | Meeting Date | Branch / Location | Meeting Title / Subject | Meeting Type | Venue / Mode | Start Time | End Time | Meeting Lead By | MOM Prepared By | Attendees Present | Absent / Regrets | Agenda Points | Discussion Summary | Key Decisions Taken | Next Meeting Date | Total Tasks | Completed | Pending | Overdue | Completion %
MOM-678 | 2026-09-09 10:30 | Conference Room 1 / Google Meet | Product Architecture & Sprint 4 Review | Project Review | Conference Room 1 / Google Meet | 04:00 PM | 05:00 PM | Harmish (Lead) | MOM Assistant | Harmish (Lead), Priya Patel (Frontend), Amit Shah (Backend), Rahul Mehta (QA) |  | 1. Sprint 4 deliverables review 2. Corporate Excel template integration for MOM export 3. Action item assignment and deadlines 4. Next release schedule | The team conducted a comprehensive sprint review focusing on backend services, document generation features, and multi-language translations. The Excel (.xlsx) export functionality based on the standard corporate template was finalized and integrated. | Approved adoption of the corporate Excel format as the standard spreadsheet export format.; Agreed on weekly automated task reminder workflow. | 2026-09-16 | 3 | 1 | 2 | 0 | 33.33%

## Tasks
Task ID | MOM ID | Meeting Date | Branch | Task / Action Point | Responsible Person | Following Person | Priority | Assigned Date | Target Deadline | Revised Deadline | Status | % Complete | Completion Date | Days Overdue (+) / Left (-) | Delay Reason | Reminder Action | Remarks | Key (system) | Overdue Flag (system)
T-001 | MOM-678 | 2026-09-01 | Head Office | Implement XLSX export endpoint and service integration | Amit Shah | Harmish (Lead) | High | 2026-09-09 10:30 | 2026-09-12 |  | Not Started | 0% | 2026-09-04 | -1 |  | Closed | Circulated on mail | MOM-001-1 | 0
T-002 | MOM-678 | 2026-09-01 | Head Office | Add Excel (.xlsx) export button in Flutter mobile interface | Priya Patel | Harmish (Lead) | High | 2026-09-09 10:30 | 2026-09-14 |  | Not Started | 0% |  | 0 | Awaiting data from other dept. | Send Reminder | Draft ready, figures pending | MOM-001-2 | 0
T-003 | MOM-678 | 2026-09-01 | Head Office | Execute end-to-end testing of generated spreadsheet with formulas | Rahul Mehta | Harmish (Lead) | Medium | 2026-09-09 10:30 | 2026-09-15 |  | Not Started | 0% |  | -12 |  | On Track |  | MOM-001-3 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Meeting Date = IF([MOM ID]="","",IFERROR(INDEX('Meetings (MOM)'!$B2:B201,MATCH([MOM ID],'Meetings (MOM)'!$A2:A201,0)),""))
Days Overdue (+) / Left (-) = IF(OR([Task ID]="",IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])=""),"",IF([Status]="Completed",IF([Completion Date]="","",[Completion Date]-IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])),IF([Status]="Cancelled","",TODAY()-IF([Revised Deadline]="",[Target Deadline],[Revised Deadline]))))
Reminder Action = IF([Task ID]="","",IF(OR([Status]="Completed",[Status]="Cancelled"),"Closed",IF(IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])="","Set deadline",IF(TODAY()>IF([Revised Deadline]="",[Target Deadline],[Revised Deadline]),"OVERDUE - Escalate",IF(IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])-TODAY()<=3,"Send Reminder","On Track")))))
Overdue Flag (system) = IF([Task ID]="",0,IF(OR([Status]="Completed",[Status]="Cancelled"),0,IF(IF([Revised Deadline]="",[Target Deadline],[Revised Deadline])="",0,IF(TODAY()>IF([Revised Deadline]="",[Target Deadline],[Revised Deadline]),1,0))))

## MOM Print
MINUTES OF MEETING
Enter MOM ID: | MOM-678 | <-- type / pick the MOM ID here, everything below fills in automatically
Meeting Date | 2026-09-01 | Branch / Location | Head Office
Meeting Title | Monthly Business Review - Aug 2026 | Meeting Type | Monthly Review
Venue / Mode | Conference Room / Zoom | Next Meeting Date | 2026-10-01
Start Time | 11:00 AM | End Time | 12:30 PM
Meeting Lead By | Mr. Director | MOM Prepared By | EA to Director
ATTENDEES PRESENT
Mr. A. Shah, Ms. P. Patel, Mr. R. Mehta
ABSENT / REGRETS
Mr. K. Joshi (on leave)
AGENDA POINTS
1. Aug sales review 2. Pending receivables 3. New branch proposal
DISCUSSION SUMMARY
Aug sales closed at 92% of target; shortfall mainly from Surat branch. Receivables above 90 days discussed - Accounts to share ageing report. Director approved in-principle survey for the new branch.
KEY DECISIONS TAKEN
Surat branch to submit recovery plan; ageing report to be circulated weekly.
ACTION POINTS / TASK LIST
Task ID | Task / Action Point | Responsible Person | Following Person | Priority | Deadline | Status | Completion
T-001 | Share 90+ days receivable ageing report with Director | Ms. P. Patel | EA to Director | High | 2026-09-05 | Completed | 100%
T-002 | Submit Surat branch sales recovery plan | Mr. R. Mehta | Mr. A. Shah | High | 2026-09-08 | In Progress | 60%
T-003 | Site survey report for proposed new branch | Mr. K. Joshi | EA to Director | Medium | 2026-09-20 | Not Started | 0%
Prepared by: | EA to Director |  | Approved by: | Mr. Director
Note: only the first 15 action points of a meeting are shown here. See the Tasks sheet for the complete list.